## Start Here
Commercial Electrical Reference 2026
2026 Submittal & Procurement Edition ¦ SignalSculpt
Workbook index
The workbook opens on Submittal Requirements because that is the primary source-backed data table. Use this index to navigate the workbook.
Tab | Primary Use | Contents | Rows | Use When
Submittal Requirements | Main data table | Equipment family, submittal type, submittal content, approval classification, section/page, source URL, and notes. | 28 | Reviewing submittal scope and coordination questions.
Equipment Reference | Equipment-family overview | Canonical equipment families with compact reference attributes and risk flags. | 21 | Starting an equipment-family review.
Risk Flags | Conservative risk classifications | Approval, testing, utility, incomplete-submittal, and schedule-critical flags tied to source evidence. | 28 | Checking schedule and review-cycle exposure.
Testing Requirements | Testing topic references | Factory, field, functional, and witness-testing topics where documented in reviewed sources. | 0 | Preparing testing and acceptance review questions.
Utility Coordination | Utility dependency references | Interconnection, metering, energization, voltage selection, application completeness, and related topics. | 0 | Reviewing utility-dependent workflow blockers.
Approval Process | Review and approval references | Approval statuses, review roles, classification markers, source sections, and notes. | 0 | Understanding documented review patterns.
Source Index | Source verification | Source organizations, source classes, document versions, retrieval dates, URLs, and row counts. | 18 | Verifying where a row came from.
Reference posture
This product is a reference workbook, not engineering advice, code interpretation, AHJ approval guidance, utility coordination guidance, procurement advice, legal advice, safety advice, or compliance certification.
Numeric lead-time fields remain blank unless a public source directly supports a numeric value.
Source URLs are preserved so buyers can verify rows against public source documents.

## Equipment Reference
Reference ID | Equipment Family | Voltage Class | Representative Submittals | Approval Notes | Utility Coordination | Applicable Risk Flags | Source URL | Note
EQ-011 | Automatic Transfer Switches (ATS) | LV | Certificates; Operations and Maintenance Manuals; Product Data; Shop Drawings; Test Reports | See Approval Process tab | Backfeed Protection | Factory or Field Testing Required; Multiple Approvals Required; Risk of Submittal Rejection; Schedule-Critical Item; Utility Coordination Required | https://ogs.ny.gov/design-construction/construction-contractors https://www.coned.com/-/media/files/coned/documents/small-medium-large-businesses/electricbluebook.pdf https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2026%2036%2023.pdf
EQ-013 | Busway / Bus Duct | LV | No source-backed submittal row yet | No approval risk flag set | No utility coordination row in current source set | No risk flag set | https://www.wbdg.org/dod/ufgs | No family-specific source row is present yet; retained as an equipment taxonomy placeholder.
EQ-014 | Cable Tray and Large Conduit | MIXED | No source-backed submittal row yet | No approval risk flag set | No utility coordination row in current source set | No risk flag set | https://www.wbdg.org/dod/ufgs | No family-specific source row is present yet; retained as an equipment taxonomy placeholder.
EQ-020 | Capacitor Banks / Harmonic Filters | MIXED | Operations and Maintenance Manuals; Product Data; Shop Drawings; Test Reports | See Approval Process tab | No utility coordination row in current source set | Factory or Field Testing Required; Multiple Approvals Required | https://www.wbdg.org/FFC/NASA/UFGS/UFGS%2026%2035%2033.00%2040.pdf
EQ-018 | Control Systems | MIXED | No source-backed submittal row yet | No approval risk flag set | Demand Response Programs | No risk flag set | https://www.coned.com/-/media/files/coned/documents/small-medium-large-businesses/electricbluebook.pdf
EQ-009 | Diesel Generators | MIXED | Certificates; Closeout Submittals; Manufacturer's Field Reports; Operations and Maintenance Manuals; Product Data; Shop Drawings; Test Reports | See Approval Process tab | Backfeed Protection; Demand Response Programs; Interconnection Requirements; Net Metering and Distributed Generation | Factory or Field Testing Required; Multiple Approvals Required; Risk of Submittal Rejection; Schedule-Critical Item; Utility Coordination Required | https://ogs.ny.gov/design-construction/construction-contractors https://www.coned.com/-/media/files/coned/documents/small-medium-large-businesses/electricbluebook.pdf https://www.dgs.ca.gov/RESD/Projects
EQ-007 | Distribution Transformers | MIXED | Certificates; Closeout Submittals; Manufacturer's Field Reports; Operations and Maintenance Manuals; Product Data; Shop Drawings; Test Reports | See Approval Process tab | Application Completeness; Utility Transformer Coordination | Factory or Field Testing Required; Multiple Approvals Required; Risk of Submittal Rejection; Schedule-Critical Item; Utility Coordination Required | https://ogs.ny.gov/design-construction/construction-contractors https://www.coned.com/-/media/files/coned/documents/small-medium-large-businesses/electricbluebook.pdf https://www.dgs.ca.gov/RESD/Projects
EQ-017 | Generator Paralleling Controls | MIXED | Closeout Submittals; Operations and Maintenance Manuals; Product Data; Shop Drawings; Test Reports | See Approval Process tab | Interconnection Requirements | Risk of Submittal Rejection; Schedule-Critical Item; Utility Coordination Required | https://ogs.ny.gov/design-construction/construction-contractors https://www.coned.com/-/media/files/coned/documents/small-medium-large-businesses/electricbluebook.pdf
EQ-003 | High Voltage Switchgear | HV | No source-backed submittal row yet | No approval risk flag set | No utility coordination row in current source set | No risk flag set | https://www.wbdg.org/dod/ufgs | No family-specific source row is present yet; retained as an equipment taxonomy placeholder.
EQ-001 | Low Voltage Switchgear (under 600V) | LV | Closeout Submittals; Operations and Maintenance Manuals; Product Data; Shop Drawings; Test Reports | See Approval Process tab | Service Voltage Selection | Factory or Field Testing Required; Multiple Approvals Required; Risk of Submittal Rejection; Schedule-Critical Item; Utility Coordination Required | https://www.coned.com/-/media/files/coned/documents/small-medium-large-businesses/electricbluebook.pdf https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2026%2023%2000.pdf
EQ-019 | Medium Voltage Motor Starters | MV | No source-backed submittal row yet | No approval risk flag set | No utility coordination row in current source set | No risk flag set | https://www.wbdg.org/dod/ufgs | No family-specific source row is present yet; retained as an equipment taxonomy placeholder.
EQ-002 | Medium Voltage Switchgear (600V to 38kV) | MV | Certificates; Manufacturer's Field Reports; Operations and Maintenance Manuals; Product Data; Shop Drawings; Test Reports | See Approval Process tab | No utility coordination row in current source set | Factory or Field Testing Required; Multiple Approvals Required; Risk of Submittal Rejection | https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2026%2013%2000.pdf
EQ-006 | Motor Control Centers (MCCs) | LV | Certificates; Product Data; Shop Drawings; Test Reports | See Approval Process tab | No utility coordination row in current source set | Factory or Field Testing Required; Multiple Approvals Required | https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2026%2028%2000.00%2010.pdf
EQ-010 | Natural Gas Generators | MIXED | Certificates; Closeout Submittals; Manufacturer's Field Reports; Operations and Maintenance Manuals; Product Data; Shop Drawings; Test Reports | See Approval Process tab | Backfeed Protection; Demand Response Programs; Interconnection Requirements; Net Metering and Distributed Generation | Factory or Field Testing Required; Multiple Approvals Required; Risk of Submittal Rejection; Schedule-Critical Item; Utility Coordination Required | https://ogs.ny.gov/design-construction/construction-contractors https://www.coned.com/-/media/files/coned/documents/small-medium-large-businesses/electricbluebook.pdf https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2026%2032%2015.pdf
EQ-005 | Panelboards | LV | Certificates; Product Data; Shop Drawings; Test Reports | See Approval Process tab | Application Completeness; Energization Authorization; Metering Decisions | Factory or Field Testing Required; Multiple Approvals Required; Schedule-Critical Item; Utility Coordination Required | https://www.coned.com/-/media/files/coned/documents/small-medium-large-businesses/electricbluebook.pdf https://www.dgs.ca.gov/RESD/Projects https://www.dgs.ca.gov/RESD/Projects/Page-Content/Projects-List-Folder/Project-9324
EQ-016 | Paralleling Switchgear | MIXED | Closeout Submittals; Operations and Maintenance Manuals; Product Data; Shop Drawings; Test Reports | See Approval Process tab | No utility coordination row in current source set | Risk of Submittal Rejection | https://ogs.ny.gov/design-construction/construction-contractors
EQ-008 | Power Transformers | MV | No source-backed submittal row yet | No approval risk flag set | No utility coordination row in current source set | No risk flag set | https://www.wbdg.org/dod/ufgs | No family-specific source row is present yet; retained as an equipment taxonomy placeholder.
EQ-015 | Secondary Unit Substations | MV | Certificates; Closeout Submittals; Manufacturer's Field Reports; Operations and Maintenance Manuals; Product Data; Shop Drawings; Test Reports | See Approval Process tab | Metering Decisions; Rate Schedule Selection; Utility Transformer Coordination | Factory or Field Testing Required; Multiple Approvals Required; Risk of Submittal Rejection; Schedule-Critical Item; Utility Coordination Required | https://www.coned.com/-/media/files/coned/documents/small-medium-large-businesses/electricbluebook.pdf https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2026%2011%2016.pdf
EQ-021 | Service Entrance Surge Protection | LV | No source-backed submittal row yet | No approval risk flag set | No utility coordination row in current source set | No risk flag set | https://www.wbdg.org/dod/ufgs | No family-specific source row is present yet; retained as an equipment taxonomy placeholder.
EQ-004 | Switchboards | LV | Certificates; Closeout Submittals; Operations and Maintenance Manuals; Product Data; Shop Drawings; Test Reports | See Approval Process tab | Application Completeness; Energization Authorization; Metering Decisions; Rate Schedule Selection; Service Voltage Selection | Factory or Field Testing Required; Multiple Approvals Required; Risk of Submittal Rejection; Schedule-Critical Item; Utility Coordination Required | https://www.coned.com/-/media/files/coned/documents/small-medium-large-businesses/electricbluebook.pdf https://www.dgs.ca.gov/RESD/Projects https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2026%2024%2013.pdf
EQ-012 | UPS Systems | MIXED | Closeout Submittals; Manufacturer's Field Reports; Operations and Maintenance Manuals; Product Data; Shop Drawings; Test Reports | See Approval Process tab | No utility coordination row in current source set | Factory or Field Testing Required; Multiple Approvals Required; Risk of Submittal Rejection | https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2026%2033%2053.pdf

## Submittal Requirements
Reference ID | Equipment Family | Submittal Type | Submittal Content | Description | Approval Classification | Source Organization | Section | Page | Document Version | Retrieved On | Source URL | Note
SUB-105 | Automatic Transfer Switches (ATS) | Shop Drawings | Shop Drawings | Documented as present in reviewed source | Not stated in source | WBDG / UFGS Federal Specifications | 26 36 23 SD-02 | 8 | february 2026 | 2026-04-27T16:21:21Z | https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2026%2036%2023.pdf
SUB-106 | Automatic Transfer Switches (ATS) | Product Data | Product Data | Documented as present in reviewed source | Not stated in source | WBDG / UFGS Federal Specifications | 26 36 23 SD-03 | 8 | february 2026 | 2026-04-27T16:21:21Z | https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2026%2036%2023.pdf
SUB-097 | Capacitor Banks / Harmonic Filters | Shop Drawings | Shop Drawings | Documented as present in reviewed source | Not stated in source | WBDG / UFGS Federal Specifications | 26 35 33.00 40 SD-02 | 5 | august 2019 | 2026-04-27T17:35:29Z | https://www.wbdg.org/FFC/NASA/UFGS/UFGS%2026%2035%2033.00%2040.pdf
SUB-098 | Capacitor Banks / Harmonic Filters | Product Data | Product Data | Documented as present in reviewed source | Not stated in source | WBDG / UFGS Federal Specifications | 26 35 33.00 40 SD-03 | 5 | august 2019 | 2026-04-27T17:35:29Z | https://www.wbdg.org/FFC/NASA/UFGS/UFGS%2026%2035%2033.00%2040.pdf
SUB-073 | Diesel Generators | Shop Drawings | Shop Drawings | Documented as present in reviewed source | Not stated in source | WBDG / UFGS Federal Specifications | 26 32 15 SD-02 | 14 | february 2026 | 2026-04-27T16:52:59Z | https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2026%2032%2015.pdf
SUB-074 | Diesel Generators | Product Data | Product Data | Documented as present in reviewed source | Not stated in source | WBDG / UFGS Federal Specifications | 26 32 15 SD-03 | 14 | february 2026 | 2026-04-27T16:52:59Z | https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2026%2032%2015.pdf
SUB-009 | Distribution Transformers | Shop Drawings | Shop Drawings | Documented as present in reviewed source | Not stated in source | WBDG / UFGS Federal Specifications | 26 11 16 SD-02 | 11 | november 2021 | 2026-04-27T16:20:45Z | https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2026%2011%2016.pdf
SUB-010 | Distribution Transformers | Product Data | Product Data | Documented as present in reviewed source | Not stated in source | WBDG / UFGS Federal Specifications | 26 11 16 SD-03 | 12 | november 2021 | 2026-04-27T16:20:45Z | https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2026%2011%2016.pdf
SUB-136 | Generator Paralleling Controls | Shop Drawings | Shop Drawings | Documented as present in reviewed source | Not stated in source | New York Office of General Services | New York Office of General Services document Ny Ogs 46187 Addendum 01 E | 2 | NY OGS Addendum 01 E 46187 | 2026-04-27T22:13:27Z | https://ogs.ny.gov/design-construction/construction-contractors
SUB-137 | Generator Paralleling Controls | Product Data | Product Data | Documented as present in reviewed source | Not stated in source | New York Office of General Services | New York Office of General Services document Ny Ogs 46187 Addendum 01 E | 2 | NY OGS Addendum 01 E 46187 | 2026-04-27T22:13:27Z | https://ogs.ny.gov/design-construction/construction-contractors
SUB-033 | Low Voltage Switchgear (under 600V) | Shop Drawings | Shop Drawings | Documented as present in reviewed source | Not stated in source | WBDG / UFGS Federal Specifications | 26 23 00 SD-02 | 9 | february 2024 | 2026-04-27T16:52:02Z | https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2026%2023%2000.pdf
SUB-034 | Low Voltage Switchgear (under 600V) | Product Data | Product Data | Documented as present in reviewed source | Not stated in source | WBDG / UFGS Federal Specifications | 26 23 00 SD-03 | 9 | february 2024 | 2026-04-27T16:52:02Z | https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2026%2023%2000.pdf
SUB-025 | Medium Voltage Switchgear (600V to 38kV) | Shop Drawings | Shop Drawings | Documented as present in reviewed source | Not stated in source | WBDG / UFGS Federal Specifications | 26 13 00 SD-02 | 7 | may 2021 change 1 05 22 | 2026-04-27T16:51:47Z | https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2026%2013%2000.pdf
SUB-026 | Medium Voltage Switchgear (600V to 38kV) | Product Data | Product Data | Documented as present in reviewed source | Not stated in source | WBDG / UFGS Federal Specifications | 26 13 00 SD-03 | 7 | may 2021 change 1 05 22 | 2026-04-27T16:51:47Z | https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2026%2013%2000.pdf
SUB-065 | Motor Control Centers (MCCs) | Shop Drawings | Shop Drawings | Documented as present in reviewed source | Not stated in source | WBDG / UFGS Federal Specifications | 26 28 00.00 10 SD-02 | 10 | february 2026 | 2026-04-27T17:34:42Z | https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2026%2028%2000.00%2010.pdf
SUB-066 | Motor Control Centers (MCCs) | Product Data | Product Data | Documented as present in reviewed source | Not stated in source | WBDG / UFGS Federal Specifications | 26 28 00.00 10 SD-03 | 10 | february 2026 | 2026-04-27T17:34:42Z | https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2026%2028%2000.00%2010.pdf
SUB-081 | Natural Gas Generators | Shop Drawings | Shop Drawings | Documented as present in reviewed source | Not stated in source | WBDG / UFGS Federal Specifications | 26 32 15 SD-02 | 14 | february 2026 | 2026-04-27T16:52:59Z | https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2026%2032%2015.pdf
SUB-082 | Natural Gas Generators | Product Data | Product Data | Documented as present in reviewed source | Not stated in source | WBDG / UFGS Federal Specifications | 26 32 15 SD-03 | 14 | february 2026 | 2026-04-27T16:52:59Z | https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2026%2032%2015.pdf
SUB-057 | Panelboards | Shop Drawings | Shop Drawings | Documented as present in reviewed source | Not stated in source | WBDG / UFGS Federal Specifications | 26 28 00.00 10 SD-02 | 10 | february 2026 | 2026-04-27T17:34:42Z | https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2026%2028%2000.00%2010.pdf
SUB-058 | Panelboards | Product Data | Product Data | Documented as present in reviewed source | Not stated in source | WBDG / UFGS Federal Specifications | 26 28 00.00 10 SD-03 | 10 | february 2026 | 2026-04-27T17:34:42Z | https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2026%2028%2000.00%2010.pdf
SUB-141 | Paralleling Switchgear | Shop Drawings | Shop Drawings | Documented as present in reviewed source | Not stated in source | New York Office of General Services | New York Office of General Services document Ny Ogs 46187 Addendum 01 E | 2 | NY OGS Addendum 01 E 46187 | 2026-04-27T22:13:27Z | https://ogs.ny.gov/design-construction/construction-contractors
SUB-142 | Paralleling Switchgear | Product Data | Product Data | Documented as present in reviewed source | Not stated in source | New York Office of General Services | New York Office of General Services document Ny Ogs 46187 Addendum 01 E | 2 | NY OGS Addendum 01 E 46187 | 2026-04-27T22:13:27Z | https://ogs.ny.gov/design-construction/construction-contractors
SUB-001 | Secondary Unit Substations | Shop Drawings | Shop Drawings | Documented as present in reviewed source | Not stated in source | WBDG / UFGS Federal Specifications | 26 11 16 SD-02 | 11 | november 2021 | 2026-04-27T16:20:45Z | https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2026%2011%2016.pdf
SUB-002 | Secondary Unit Substations | Product Data | Product Data | Documented as present in reviewed source | Not stated in source | WBDG / UFGS Federal Specifications | 26 11 16 SD-03 | 12 | november 2021 | 2026-04-27T16:20:45Z | https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2026%2011%2016.pdf
SUB-041 | Switchboards | Shop Drawings | Shop Drawings | Documented as present in reviewed source | Not stated in source | WBDG / UFGS Federal Specifications | 26 24 13 SD-02 | 8 | august 2021 | 2026-04-27T16:52:20Z | https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2026%2024%2013.pdf
SUB-042 | Switchboards | Product Data | Product Data | Documented as present in reviewed source | Not stated in source | WBDG / UFGS Federal Specifications | 26 24 13 SD-03 | 8 | august 2021 | 2026-04-27T16:52:20Z | https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2026%2024%2013.pdf
SUB-089 | UPS Systems | Shop Drawings | Shop Drawings | Documented as present in reviewed source | Not stated in source | WBDG / UFGS Federal Specifications | 26 33 53 SD-02 | 9 | august 2025 | 2026-04-27T16:53:50Z | https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2026%2033%2053.pdf
SUB-090 | UPS Systems | Product Data | Product Data | Documented as present in reviewed source | Not stated in source | WBDG / UFGS Federal Specifications | 26 33 53 SD-03 | 9 | august 2025 | 2026-04-27T16:53:50Z | https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2026%2033%2053.pdf

## Approval Process
No Rows

## Testing Requirements
No Rows

## Utility Coordination
No Rows

## Risk Flags
Reference ID | Equipment Family | Risk Flag | Flag Status | Confidence Level | Methodology Note | Source Evidence | Source Organization | Source Class | Source URL
RSK-001 | Automatic Transfer Switches (ATS) | Multiple Approvals Required | Flag Set | High | Flag set when reviewed sources show multiple submittal items, an approval marker, and named review roles. | WBDG / UFGS Federal Specifications, Section UFGS 01 33 00 approval authority, page 5; WBDG / UFGS Federal Specifications, Section UFGS 01 33 00 approval authority, page 15; WBDG / UFGS Federal Specifications, Section 26 36 23 approval classification, page 8; WBDG / UFGS Federal Specifications, Section 26 36 23 SD-03, page 8 | WBDG / UFGS Federal Specifications | Federal Specification | https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2001%2033%2000.pdf https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2026%2036%2023.pdf
RSK-002 | Automatic Transfer Switches (ATS) | Risk of Submittal Rejection | Flag Set | High | Flag set when reviewed sources show several submittal content types and revise-and-resubmit status context. | WBDG / UFGS Federal Specifications, Section UFGS 01 33 00 status notations, page 33; WBDG / UFGS Federal Specifications, Section 26 36 23 SD-07, page 8; WBDG / UFGS Federal Specifications, Section 26 36 23 SD-10, page 8; WBDG / UFGS Federal Specifications, Section 26 36 23 SD-03, page 8 | WBDG / UFGS Federal Specifications | Federal Specification | https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2001%2033%2000.pdf https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2026%2036%2023.pdf
RSK-010 | Capacitor Banks / Harmonic Filters | Multiple Approvals Required | Flag Set | High | Flag set when reviewed sources show multiple submittal items, an approval marker, and named review roles. | WBDG / UFGS Federal Specifications, Section UFGS 01 33 00 approval authority, page 5; WBDG / UFGS Federal Specifications, Section UFGS 01 33 00 approval authority, page 15; WBDG / UFGS Federal Specifications, Section 26 35 33.00 40 approval classification, page 5; WBDG / UFGS Federal Specifications, Section 26 35 33.00 40 SD-03, page 5 | WBDG / UFGS Federal Specifications | Federal Specification | https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2001%2033%2000.pdf https://www.wbdg.org/FFC/NASA/UFGS/UFGS%2026%2035%2033.00%2040.pdf
RSK-011 | Capacitor Banks / Harmonic Filters | Factory or Field Testing Required | Flag Set | Moderate | Flag set when a reviewed source documents factory, field, functional, or witness testing for the equipment family. | WBDG / UFGS Federal Specifications, Section 26 35 33.00 40 testing requirements, page 6 | WBDG / UFGS Federal Specifications | Federal Specification | https://www.wbdg.org/FFC/NASA/UFGS/UFGS%2026%2035%2033.00%2040.pdf
RSK-013 | Diesel Generators | Multiple Approvals Required | Flag Set | High | Flag set when reviewed sources show multiple submittal items, an approval marker, and named review roles. | WBDG / UFGS Federal Specifications, Section UFGS 01 33 00 approval authority, page 5; WBDG / UFGS Federal Specifications, Section UFGS 01 33 00 approval authority, page 15; WBDG / UFGS Federal Specifications, Section 26 32 15 approval classification, page 14; WBDG / UFGS Federal Specifications, Section 26 32 15 SD-03, page 14 | WBDG / UFGS Federal Specifications | Federal Specification | https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2001%2033%2000.pdf https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2026%2032%2015.pdf
RSK-014 | Diesel Generators | Risk of Submittal Rejection | Flag Set | High | Flag set when reviewed sources show several submittal content types and revise-and-resubmit status context. | WBDG / UFGS Federal Specifications, Section UFGS 01 33 00 status notations, page 33; WBDG / UFGS Federal Specifications, Section 26 32 15 SD-07, page 16; WBDG / UFGS Federal Specifications, Section 26 32 15 SD-09, page 16; WBDG / UFGS Federal Specifications, Section 26 32 15 SD-10, page 16 | WBDG / UFGS Federal Specifications | Federal Specification | https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2001%2033%2000.pdf https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2026%2032%2015.pdf
RSK-024 | Distribution Transformers | Multiple Approvals Required | Flag Set | High | Flag set when reviewed sources show multiple submittal items, an approval marker, and named review roles. | WBDG / UFGS Federal Specifications, Section UFGS 01 33 00 approval authority, page 5; WBDG / UFGS Federal Specifications, Section UFGS 01 33 00 approval authority, page 15; WBDG / UFGS Federal Specifications, Section 26 11 16 approval classification, page 10; WBDG / UFGS Federal Specifications, Section 26 11 16 SD-03, page 12 | WBDG / UFGS Federal Specifications | Federal Specification | https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2001%2033%2000.pdf https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2026%2011%2016.pdf https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2026%2012%2019.pdf
RSK-025 | Distribution Transformers | Risk of Submittal Rejection | Flag Set | High | Flag set when reviewed sources show several submittal content types and revise-and-resubmit status context. | WBDG / UFGS Federal Specifications, Section UFGS 01 33 00 status notations, page 33; WBDG / UFGS Federal Specifications, Section 26 11 16 SD-07, page 12; WBDG / UFGS Federal Specifications, Section 26 11 16 SD-09, page 12; WBDG / UFGS Federal Specifications, Section 26 11 16 SD-10, page 13 | WBDG / UFGS Federal Specifications | Federal Specification | https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2001%2033%2000.pdf https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2026%2011%2016.pdf
RSK-036 | Generator Paralleling Controls | Risk of Submittal Rejection | Flag Set | High | Flag set when reviewed sources show several submittal content types and revise-and-resubmit status context. | WBDG / UFGS Federal Specifications, Section UFGS 01 33 00 status notations, page 33; New York Office of General Services, Section document Ny Ogs 46187 Addendum 01 E, page 3; New York Office of General Services, Section document Ny Ogs 46187 Addendum 01 E, page 3; New York Office of General Services, Section document Ny Ogs 46187 Addendum 01 E, page 2 | WBDG / UFGS Federal Specifications | Multi-Source Reference | https://ogs.ny.gov/design-construction/construction-contractors https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2001%2033%2000.pdf
RSK-037 | Generator Paralleling Controls | Schedule-Critical Item | Flag Set | High | Flag set when utility coordination evidence appears with another schedule-related source pattern for the same equipment family. | WBDG / UFGS Federal Specifications, Section UFGS 01 33 00 status notations, page 33; New York Office of General Services, Section document Ny Ogs 46187 Addendum 01 E, page 3; Con Edison Blue Book, Section Con Edison Blue Book Section V, page 59 | WBDG / UFGS Federal Specifications | Multi-Source Reference | https://ogs.ny.gov/design-construction/construction-contractors https://www.coned.com/-/media/files/coned/documents/small-medium-large-businesses/electricbluebook.pdf https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2001%2033%2000.pdf
RSK-040 | Low Voltage Switchgear (under 600V) | Multiple Approvals Required | Flag Set | High | Flag set when reviewed sources show multiple submittal items, an approval marker, and named review roles. | WBDG / UFGS Federal Specifications, Section UFGS 01 33 00 approval authority, page 5; WBDG / UFGS Federal Specifications, Section UFGS 01 33 00 approval authority, page 15; WBDG / UFGS Federal Specifications, Section 26 23 00 approval classification, page 9; WBDG / UFGS Federal Specifications, Section 26 23 00 SD-03, page 9 | WBDG / UFGS Federal Specifications | Federal Specification | https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2001%2033%2000.pdf https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2026%2023%2000.pdf
RSK-041 | Low Voltage Switchgear (under 600V) | Risk of Submittal Rejection | Flag Set | High | Flag set when reviewed sources show several submittal content types and revise-and-resubmit status context. | WBDG / UFGS Federal Specifications, Section UFGS 01 33 00 status notations, page 33; WBDG / UFGS Federal Specifications, Section 26 23 00 SD-11, page 9; WBDG / UFGS Federal Specifications, Section 26 23 00 SD-10, page 9; WBDG / UFGS Federal Specifications, Section 26 23 00 SD-03, page 9 | WBDG / UFGS Federal Specifications | Federal Specification | https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2001%2033%2000.pdf https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2026%2023%2000.pdf
RSK-047 | Medium Voltage Switchgear (600V to 38kV) | Multiple Approvals Required | Flag Set | High | Flag set when reviewed sources show multiple submittal items, an approval marker, and named review roles. | WBDG / UFGS Federal Specifications, Section UFGS 01 33 00 approval authority, page 5; WBDG / UFGS Federal Specifications, Section UFGS 01 33 00 approval authority, page 15; WBDG / UFGS Federal Specifications, Section 26 13 00 approval classification, page 7; WBDG / UFGS Federal Specifications, Section 26 13 00 SD-03, page 7 | WBDG / UFGS Federal Specifications | Federal Specification | https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2001%2033%2000.pdf https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2026%2013%2000.pdf
RSK-048 | Medium Voltage Switchgear (600V to 38kV) | Risk of Submittal Rejection | Flag Set | High | Flag set when reviewed sources show several submittal content types and revise-and-resubmit status context. | WBDG / UFGS Federal Specifications, Section UFGS 01 33 00 status notations, page 33; WBDG / UFGS Federal Specifications, Section 26 13 00 SD-07, page 8; WBDG / UFGS Federal Specifications, Section 26 13 00 SD-09, page 8; WBDG / UFGS Federal Specifications, Section 26 13 00 SD-10, page 8 | WBDG / UFGS Federal Specifications | Federal Specification | https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2001%2033%2000.pdf https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2026%2013%2000.pdf
RSK-051 | Motor Control Centers (MCCs) | Multiple Approvals Required | Flag Set | High | Flag set when reviewed sources show multiple submittal items, an approval marker, and named review roles. | WBDG / UFGS Federal Specifications, Section UFGS 01 33 00 approval authority, page 5; WBDG / UFGS Federal Specifications, Section UFGS 01 33 00 approval authority, page 15; WBDG / UFGS Federal Specifications, Section 26 28 00.00 10 approval classification, page 10; WBDG / UFGS Federal Specifications, Section 26 28 00.00 10 SD-03, page 10 | WBDG / UFGS Federal Specifications | Federal Specification | https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2001%2033%2000.pdf https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2026%2028%2000.00%2010.pdf
RSK-052 | Motor Control Centers (MCCs) | Factory or Field Testing Required | Flag Set | Moderate | Flag set when a reviewed source documents factory, field, functional, or witness testing for the equipment family. | WBDG / UFGS Federal Specifications, Section 26 28 00.00 10 testing requirements, page 2 | WBDG / UFGS Federal Specifications | Federal Specification | https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2026%2028%2000.00%2010.pdf
RSK-054 | Natural Gas Generators | Multiple Approvals Required | Flag Set | High | Flag set when reviewed sources show multiple submittal items, an approval marker, and named review roles. | WBDG / UFGS Federal Specifications, Section UFGS 01 33 00 approval authority, page 5; WBDG / UFGS Federal Specifications, Section UFGS 01 33 00 approval authority, page 15; WBDG / UFGS Federal Specifications, Section 26 32 15 approval classification, page 14; WBDG / UFGS Federal Specifications, Section 26 32 15 SD-03, page 14 | WBDG / UFGS Federal Specifications | Federal Specification | https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2001%2033%2000.pdf https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2026%2032%2015.pdf
RSK-055 | Natural Gas Generators | Risk of Submittal Rejection | Flag Set | High | Flag set when reviewed sources show several submittal content types and revise-and-resubmit status context. | WBDG / UFGS Federal Specifications, Section UFGS 01 33 00 status notations, page 33; WBDG / UFGS Federal Specifications, Section 26 32 15 SD-07, page 16; WBDG / UFGS Federal Specifications, Section 26 32 15 SD-09, page 16; WBDG / UFGS Federal Specifications, Section 26 32 15 SD-10, page 16 | WBDG / UFGS Federal Specifications | Federal Specification | https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2001%2033%2000.pdf https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2026%2032%2015.pdf
RSK-065 | Panelboards | Multiple Approvals Required | Flag Set | High | Flag set when reviewed sources show multiple submittal items, an approval marker, and named review roles. | WBDG / UFGS Federal Specifications, Section UFGS 01 33 00 approval authority, page 5; WBDG / UFGS Federal Specifications, Section UFGS 01 33 00 approval authority, page 15; WBDG / UFGS Federal Specifications, Section 26 28 00.00 10 approval classification, page 10; WBDG / UFGS Federal Specifications, Section 26 28 00.00 10 SD-03, page 10 | WBDG / UFGS Federal Specifications | Federal Specification | https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2001%2033%2000.pdf https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2026%2028%2000.00%2010.pdf
RSK-066 | Panelboards | Long Lead Time Equipment | No Flag Set | No Flag Set - Source Evidence Reviewed | No explicit source-backed long lead wording was found in the reviewed sources. | WBDG / UFGS Federal Specifications, Section 26 28 00.00 10 SD-02, page 10; VA Construction and Facilities Management, Section document Va 26 24 16 Master Spec, page 2; Con Edison Blue Book, Section Con Edison Blue Book Quick Start / Section I.C, page 3 | WBDG / UFGS Federal Specifications | Multi-Source Reference | https://www.coned.com/-/media/files/coned/documents/small-medium-large-businesses/electricbluebook.pdf https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2026%2028%2000.00%2010.pdf https://www.wbdg.org/va/va-master-specifications-pg-18-1/va-26-24-16
RSK-074 | Paralleling Switchgear | Risk of Submittal Rejection | Flag Set | High | Flag set when reviewed sources show several submittal content types and revise-and-resubmit status context. | WBDG / UFGS Federal Specifications, Section UFGS 01 33 00 status notations, page 33; New York Office of General Services, Section document Ny Ogs 46187 Addendum 01 E, page 3; New York Office of General Services, Section document Ny Ogs 46187 Addendum 01 E, page 3; New York Office of General Services, Section document Ny Ogs 46187 Addendum 01 E, page 2 | WBDG / UFGS Federal Specifications | Multi-Source Reference | https://ogs.ny.gov/design-construction/construction-contractors https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2001%2033%2000.pdf
RSK-075 | Paralleling Switchgear | Long Lead Time Equipment | No Flag Set | No Flag Set - Source Evidence Reviewed | No explicit source-backed long lead wording was found in the reviewed sources. | New York Office of General Services, Section document Ny Ogs 46187 Addendum 01 E, page 2 | New York Office of General Services | State Public Document | https://ogs.ny.gov/design-construction/construction-contractors
RSK-077 | Secondary Unit Substations | Multiple Approvals Required | Flag Set | High | Flag set when reviewed sources show multiple submittal items, an approval marker, and named review roles. | WBDG / UFGS Federal Specifications, Section UFGS 01 33 00 approval authority, page 5; WBDG / UFGS Federal Specifications, Section UFGS 01 33 00 approval authority, page 15; WBDG / UFGS Federal Specifications, Section 26 11 16 approval classification, page 10; WBDG / UFGS Federal Specifications, Section 26 11 16 SD-03, page 12 | WBDG / UFGS Federal Specifications | Federal Specification | https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2001%2033%2000.pdf https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2026%2011%2016.pdf
RSK-078 | Secondary Unit Substations | Risk of Submittal Rejection | Flag Set | High | Flag set when reviewed sources show several submittal content types and revise-and-resubmit status context. | WBDG / UFGS Federal Specifications, Section UFGS 01 33 00 status notations, page 33; WBDG / UFGS Federal Specifications, Section 26 11 16 SD-07, page 12; WBDG / UFGS Federal Specifications, Section 26 11 16 SD-09, page 12; WBDG / UFGS Federal Specifications, Section 26 11 16 SD-10, page 13 | WBDG / UFGS Federal Specifications | Federal Specification | https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2001%2033%2000.pdf https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2026%2011%2016.pdf
RSK-086 | Switchboards | Multiple Approvals Required | Flag Set | High | Flag set when reviewed sources show multiple submittal items, an approval marker, and named review roles. | WBDG / UFGS Federal Specifications, Section UFGS 01 33 00 approval authority, page 5; WBDG / UFGS Federal Specifications, Section UFGS 01 33 00 approval authority, page 15; WBDG / UFGS Federal Specifications, Section 26 24 13 approval classification, page 8; WBDG / UFGS Federal Specifications, Section 26 24 13 SD-03, page 8 | WBDG / UFGS Federal Specifications | Federal Specification | https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2001%2033%2000.pdf https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2026%2024%2013.pdf https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2026%2028%2000.00%2010.pdf
RSK-087 | Switchboards | Risk of Submittal Rejection | Flag Set | High | Flag set when reviewed sources show several submittal content types and revise-and-resubmit status context. | WBDG / UFGS Federal Specifications, Section UFGS 01 33 00 status notations, page 33; WBDG / UFGS Federal Specifications, Section 26 24 13 SD-07, page 8; WBDG / UFGS Federal Specifications, Section 26 24 13 SD-11, page 8; WBDG / UFGS Federal Specifications, Section 26 24 13 SD-10, page 8 | WBDG / UFGS Federal Specifications | Federal Specification | https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2001%2033%2000.pdf https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2026%2024%2013.pdf
RSK-099 | UPS Systems | Multiple Approvals Required | Flag Set | High | Flag set when reviewed sources show multiple submittal items, an approval marker, and named review roles. | WBDG / UFGS Federal Specifications, Section UFGS 01 33 00 approval authority, page 5; WBDG / UFGS Federal Specifications, Section UFGS 01 33 00 approval authority, page 15; WBDG / UFGS Federal Specifications, Section 26 33 53 approval classification, page 9; WBDG / UFGS Federal Specifications, Section 26 33 53 SD-03, page 9 | WBDG / UFGS Federal Specifications | Federal Specification | https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2001%2033%2000.pdf https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2026%2033%2053.pdf
RSK-100 | UPS Systems | Risk of Submittal Rejection | Flag Set | High | Flag set when reviewed sources show several submittal content types and revise-and-resubmit status context. | WBDG / UFGS Federal Specifications, Section UFGS 01 33 00 status notations, page 33; WBDG / UFGS Federal Specifications, Section 26 33 53 SD-11, page 10; WBDG / UFGS Federal Specifications, Section 26 33 53 SD-09, page 10; WBDG / UFGS Federal Specifications, Section 26 33 53 SD-10, page 10 | WBDG / UFGS Federal Specifications | Federal Specification | https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2001%2033%2000.pdf https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2026%2033%2053.pdf

## Source Index
Reference ID | Source Organization | Source Class | Document Version | Retrieved On | Source URL | Rows Citing Source
SRC-001 | California Division of the State Architect | State Public Document | California DGS Project Addendum No. 2 | 2026-04-27T20:47:58Z | https://www.dgs.ca.gov/RESD/Projects/Page-Content/Projects-List-Folder/Project-9324 | 1
SRC-002 | California Division of the State Architect | State Public Document | California DGS Project Manual Book III 24-235656 | 2026-04-27T21:23:06Z | https://www.dgs.ca.gov/RESD/Projects | 4
SRC-003 | Con Edison Blue Book | Utility Manual | 2026 Edition Revised January 2026 | 2026-04-28T01:23:16Z | https://www.coned.com/-/media/files/coned/documents/small-medium-large-businesses/electricbluebook.pdf | 25
SRC-004 | New York Office of General Services | State Public Document | NY OGS Addendum 01 CHE | 2026-04-27T22:15:48Z | https://ogs.ny.gov/design-construction/construction-contractors | 18
SRC-005 | New York Office of General Services | State Public Document | NY OGS Addendum 01 E | 2026-04-27T22:13:22Z | https://ogs.ny.gov/design-construction/construction-contractors | 5
SRC-006 | New York Office of General Services | State Public Document | NY OGS Addendum 01 E 46187 | 2026-04-27T22:13:27Z | https://ogs.ny.gov/design-construction/construction-contractors | 20
SRC-007 | VA Construction and Facilities Management | Federal Specification | VA Master Specification 26 24 16 Panelboards | 2026-04-27T21:14:39Z | https://www.wbdg.org/va/va-master-specifications-pg-18-1/va-26-24-16 | 2
SRC-010 | WBDG / UFGS Federal Specifications | Federal Specification | August 2018 Change 4 - 02/21 | 2026-04-27T15:13:05Z | https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2001%2033%2000.pdf | 23
SRC-011 | WBDG / UFGS Federal Specifications | Federal Specification | august 2019 | 2026-04-27T17:35:29Z | https://www.wbdg.org/FFC/NASA/UFGS/UFGS%2026%2035%2033.00%2040.pdf | 13
SRC-012 | WBDG / UFGS Federal Specifications | Federal Specification | august 2021 | 2026-04-27T16:52:20Z | https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2026%2024%2013.pdf | 13
SRC-013 | WBDG / UFGS Federal Specifications | Federal Specification | august 2025 | 2026-04-27T16:53:50Z | https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2026%2033%2053.pdf | 13
SRC-014 | WBDG / UFGS Federal Specifications | Federal Specification | february 2024 | 2026-04-27T16:52:02Z | https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2026%2023%2000.pdf | 13
SRC-015 | WBDG / UFGS Federal Specifications | Federal Specification | february 2026 | 2026-04-27T17:34:42Z | https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2026%2028%2000.00%2010.pdf | 39
SRC-016 | WBDG / UFGS Federal Specifications | Federal Specification | february 2026 | 2026-04-27T16:52:59Z | https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2026%2032%2015.pdf | 26
SRC-017 | WBDG / UFGS Federal Specifications | Federal Specification | february 2026 | 2026-04-27T16:21:21Z | https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2026%2036%2023.pdf | 13
SRC-018 | WBDG / UFGS Federal Specifications | Federal Specification | may 2021 change 1 05 22 | 2026-04-27T16:51:47Z | https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2026%2013%2000.pdf | 13
SRC-019 | WBDG / UFGS Federal Specifications | Federal Specification | may 2024 change 2 11 23 | 2026-04-27T16:51:32Z | https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2026%2012%2019.pdf | 13
SRC-020 | WBDG / UFGS Federal Specifications | Federal Specification | november 2021 | 2026-04-27T16:20:45Z | https://www.wbdg.org/FFC/DOD/UFGS/UFGS%2026%2011%2016.pdf | 26

## Methodology
Topic | Explanation
Source Selection | This reference pack uses public federal specifications, public agency documents, state public documents, and utility service manuals.
Conservative Claims | Rows are included when the source supports the reference pattern. Ambiguous findings are left blank or marked with a note.
Lead Time Policy | Numeric lead time fields stay blank unless a public source directly states the value.
Source Gaps | Some target sections were not publicly retrievable. Gaps are documented instead of filling rows by estimate.
Buyer Use | Use this workbook to prepare questions, compare source patterns, and review submittal, approval, testing, and utility coordination topics.

## Limitations and Disclaimer
Topic | Explanation
Reference Only | This product is not engineering advice, code interpretation, utility approval guidance, procurement advice, or compliance certification.
Project Review | Project-specific decisions remain with licensed professionals, owners, contractors, utilities, and authorities having jurisdiction.
Source Changes | Public source documents may change, move, or be withdrawn. Source URLs are preserved so buyers can review current documents.
No Approval Promise | The reference pack does not promise that any authority, owner, utility, or reviewer will accept a submittal or project decision.